## GL Changes
Item | JDE Changes | Questions | TO DO | Payroll To Do List | Coding Change Status
General Leave
Add Floating Holiday | Add second floating holiday to all employees |  | Hard code 20.00 hours for PD and General and 28 hours for Fire shift- Sheryl will hardcode | Add to validation table | Deployed to DV for testing 7/21/23. Added 20 and 28 hours to R55146LU2 for early booking of 2024 and R55146LU3 for ongoing program beginning 2024. Validation for floating holiday limit is retrieved from the 8013 pdba in the leave table and isn't hard coded.
General Leave Accrual Rates | Accrual rates follow the original accural rates (DBA 8000 and 8050) with no limit at 10 years. DBA 8001 and 8051 stops at 10 years |  | Remove all employees from 8001 and 8051 and move them into 8000 or 8050 to allow for the acccruals to continue up to the 20 year accrual amount | Review to make sure employees have been moved. Audit to verify that all employees have GL accrual on the first pay date in January
DBA's
Working a Holiday earns 1.5x pay rate | Create new pay type with 1.5 multiplier |  | New Paycode for holiday worked with 1.5 multiplier. - 958 for Gen, 968 for PD, and 9978 for Fire. These will be for all non-exempt employees. NB employees will also receive 1.5x for working on a holiday. Do we need another paytype?? Ould we use 958 for NB EE's? Yes but they would need to convert to 407 or anotherh .5 pay code not the same as benefitted. We need to add this to the sick leave accrual DBA for NB. It will also need to roll up into the pensionable calculation | Add 3 codes to validation groups. Verify that all codes calculate correctly
Bereavement | Add new DBA code 136 |  | Created new code 136 for Bereavement to use starting 2024. This is so 135 (original DBA) is deducted from GL and 136 will not be. | Add to validation groups and make sure hours are not deducted from GL bank
Admin Leave | Staying for 2024
New Employee Leave | Staying for 2024
Sick Leave | DBA 125 - will need new accrual code to begin 1/1/24. Sick time will be in separate bank from vacation leave |  | Created Calculation Table 8030 using a custom table method UA. The values in the table represent days since Part Date and UDC #14. This field will be populated with 1/1/xx at the beginning of each year BEFORE the 1st pay period of the year. Will pro-rate accrual for sick time based on how many pay periods are remaining. |  | 8021- Summary DBA for Sick Leave. Add 125, 126 for Basis of Calc 8030- Sick Leave Earn (Gen EEs) and 8031 Sick Leave Earn (Fire EEs)- use Calculation Table
Paid FMLA | Code 126 FMLA Sick and new code 128 FMLA vacation |  | No, but we do need a new summary DBA for the new leave bank for PD and Gen. Just the sick leave code. Added new summary DBA= Sick Lv Taken DBA- 8021 with 125 and 126 in the basis of calc. | Add 126 and 128 to validation tables | Rename pay code for FMLA-SICK (126)- add to 8021, Create pay code for FMLA-VAC (128)- copy 126 and add to 8023
Vacation Taken | New Summary PDBA 8023
Vacation Rollover Limit | Change purpurse of 8008 and 8056 |  | PDBA table for calculation needs changed at implementation. Should calculate and adjust for FTE |  | Data needed to test leave update. Not critical for 1/1/24 but could be done soon after 1st of year.
New GL Leave Display | New form P55GLV01¦W55GLV01B |  | Validate form content
Benefit Plan Changes
Flex Admin | Rate changing for 2024 |  | HR to make changes to JDE once final check is processed in 2023. Changes will begin on first check in 2024 | Verify that 1/5/24 check processes new admin fee. $.87 is new rate per pay period
Flexible Spending/RMR
ARAG Premium | Rate changing for 2024 |  | HR to make changes to JDE once final check is processed in 2023. Changes will begin on first check in 2024 | Verify that 1/5/24 check processes new admin fee. Rates are $18.25/month and $21.90/month
Insurance Premiums | Moving to paying premiums current. Also changing premium structure to eliminate exempt vs non-exempt rates and change part time premiums. |  | Stop all wellness, medical, dental, and vision premiums from calculating for both December checks. Then prior to 1/1/24, change premium table to new rates and turn all premium calculations back on. | Verify that no premiums calculate in December and new premiums calculate in January. Also, verify that new rates are working in January. Premiums are due based on start and term dates. If start 1-15th of month, EE's pay full premiums due for month, if 16-EOM then no premiums for month. Effective date is date of hire. If terminating 1-15th the EE does not pay premiums for month, if 16-EOM then EE's pay full month. Cancel date of insurance is separation date.
Pension Rates |  |  | HR to increase the EE and ER pension rates between 12/21/23 and 12/31/23 | Verify that all pension rates are increased for the first check in January. EE will be 11.5% and ER will be 11.75%
FPPA Rates/D&D |  |  | HR to increase the EE and ER pension rates between 1/3/24 and 1/12/24 | Verify that all FPPA pension rates as well as the D&D rates are adjusted for the second check in January
Critical Care/Accident Insurance |  |  | Set up new codes for Critical care and Accident Insurance prior to 12/31/23 | Verify that the new critical care and accident insurance are processed on the 1/5/24 check. Both are new benefits.
General Leave Cashout
48 Hour Cash Out 2023 | No Changes- all cash outs will go 100% DC and we have a pay code |  |  | Fire and PD with CBA are allowed to cashout up to 48 hours at 100% pay if putting into 457 plan. Checks are processed on 11/3/23. Need to also review maximum contribution limits as processing these payments.
GL Cashout for 2023 (@ 50%) | Cashout General leave balances over 280 (392 for Fire). |  |  | Will complete two interims to cashout general leave for all employees to get their balances to 280 for general and police or 392 for Fire. Code 186 will be used which pays out at 50%. Employees can choose to have this done in 2023 or 2024 and can take cash or put into the deferred comp. They can also do a mixture of all. Forms will be turned into payroll by December 6th to complete interim on December 15th. Second interim will be January 26th and will include those that opted for 2024 cashout OR anyone that was over maximum amounts that did not complete a form. Those without a form will be completed as cash. Both payments will be completed as direct deposits. An audit will be completed after January 3rd to ensure we cashout all leave down to the maximum allowable.
Vacation Cashout- End of Year | In 2024 cashout vacation hours at end of year |  | Cashout for 48 hours applies to only the EEs covered by the CBA (2023). Cashout for 48 + 32 hours applies to all EEs in 2024 | The 100% cashout code that would tax at the supplemental pay is 176 which is what we use when putting their payment into DC.
Report for payroll to use at the end of each year. Vacation and sick leave balances to determine whether or not an employee has used less than 41 hours of sick leave
One Time Cashout | Last pay period in December 2023 and/or first pay period in January 2023 |  |  | Will be on interim. Working with mgmt to get dates
Miscellaneous
Overtime Calculation | Remove some DBAs (TBD)
Comp Time | Limit is 80 and not 60. Not sure if we need to make any changes for this |  |  | No adjustment needed. This is a manual process that Payroll does each quarter.
Disable pay codes in timesheet application |  |  |  | Work to HR to remove DBA codes that we are no longer using from timesheets.
Vacation Changes | Change current accrual/earn plans and create a new ones |  |  | Set up new Vacation Summary DBA (8023). Leave 8016 Gen Taken 'as is' so that when employees go back in history the time is reflected correctly. The new DBA (8023) Basis of Calc will have only the pay types that will decrement the vacation bank moving forward. | No one has the Taken Summary DBAs in their DBA Instructions- they work behind the scenes in the Leave Update program, 8023- New Vacation Taken Summary DBA (2024+) Adjust the Basis of Calc table with the correct/revised pay code list
| Remove the GEN GRT and GEN GRT2 from EEs |  | Create a new plan for GEN HOLIDAY- with 8010- SHOULD 8010 have a table that calculates 100 hours? Currently has 96.00 |  | We do not need 8010, so we will un enroll everyone from GEN GRT, GEN GRT2 and FIRE GRT.
Employees are enrolled in HOL GEN (8017) and HOL FIre (8061). These DBAs calculate 100 or 140 for the 10 holidays.
Mark the EEs with GEN GRT and GEN GRT2 with a flag in Cat Code 10 (P010) and re- enroll into HOL EARN
| Determine what payroll or when the rollovers with happen each year |  |  | Will work with mgmt team to get dates each year
Vacation Rollover | Code to remove the extra hours at the end of the year |  | Create a DBA to reduce the banks at a zero dollar amount- similar to GL Share (146)